## a) All Sites
a) All Sites - Summary of Actual and Forecast Completions
[15 empty] | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
| Total (Net) | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total
Completions 1/4/11 to 31/3/24 (Net) | 10154 | 144 | 262 | 294 | 732 | 619 | 1094 | 1031 | 1050 | 1168 | 841 | 1111 | 915 | 893 | 0 | 0 | 0 | 0 | 0 | 10154
b1) Commitments (outline) @ April 2024 (Net) | 3861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 160 | 260 | 360 | 402 | 1192
b2) Commitments (full permission) @ April 2024 (Net) | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 632 | 541 | 370 | 206 | 2525
b3i) Commitments - Residential Institutions @ April 2024 (Net) | 43.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.386 | 14.386 | 14.386 | 0 | 0 | 43.1579
b3ii) Commitments - Students and HMOs @ April 2024 (Net) | 107.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.9722 | 35.9722 | 35.9722 | 0 | 0 | 107.9167
c) Small Urban SHLAA Sites (Less 10% - rounded) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d) Windfall Allowance | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101 | 101 | 101 | 101 | 101 | 505
e) Canalside & Employment Regen Areas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f) Allocated Brownfield Sites without permission | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 184 | 267
g) Allocated Greenfield Sites without permission | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 45 | 55
h) Allocated Sites Villages without permission | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 49 | 12 | 0 | 71
Total | 17717.0746 | 144 | 262 | 294 | 732 | 619 | 1094 | 1031 | 1050 | 1168 | 841 | 1111 | 915 | 893 | 937.3582 | 953.3582 | 1001.3582 | 936 | 938 | 14920.0746
Cumulative Total |  | 144 | 406 | 700 | 1432 | 2051 | 3145 | 4176 | 5226 | 6394 | 7235 | 8346 | 9261 | 10154 | 11091.3582 | 12044.7164 | 13046.0746 | 13982.0746 | 14920.0746
Housing Trajectory 2011 - 2029
Year |  | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29
Actual Completions |  | 144 | 262 | 294 | 732 | 619 | 1094 | 1031 | 1050 | 1168 | 841 | 1111 | 915 | 893
Forecast Completions |  | 2024/25: 937.3582; 2025/26: 953.3582; 2026/27: 1001.3582; 2027/28: 936; 2028/29: 938
Average Annual Requirement |  | 600 | 600 | 600 | 600 | 600 | 600 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098 | 1098
Five Year Supply
Requirement Calculations
Average annual requirement 1/4/11 to 31/3/17 | 600
Average annual requirement 1/4/17 to 31/3/29 | 1098
Requirement to date (1/4/11 to 31/3/24) (Local Plan figures only) | 11286
Completions to date (1/4/11 to 31/3/24) | 10154
Total requirement over the next 5 years (1/4/24 to 31/3/29) based on the latest Dec 2024 NPPF Standard Method annual requirement figure for WDC of 1062 dwellings per annum (utilising 2023 affordability ratios published in March 2024) | 5310
Buffer - either a 5% buffer to ensure choice and competition or 20% buffer where there is significant under-delivery over the 3 previous years. (5% applied for 2024) | 265.5
TOTAL 5 YEAR REQUIREMENT | 5575.5
ANNUAL 5 YEAR REQUIREMENT | 1115.1
Supply Calculations next five years (1/4/24 to 31/3/29)
Commitments - Planning Permissions | 3717
Commitments - Residential Institutions (@1.9 residents per dwelling) | 43.1579
Commitments - Students and HMOs (@2.4 students per dwelling) | 107.9167
Small Urban SHLAA Sites | 0
Windfalls | 505
Consolidated employment land (Canalside and Employment areas tab) | 0
Local Plan Allocations without permission | 393
Total 5 YEAR SUPPLY (1/4/24 to 31/3/29) | 4766.0746 | 2012/13: NB the above Housing Trajectory graph and associated table reflects the Local Plan requirements, rather than the Standard Method requirements implemented since 2023
Contribution towards meeting Coventry unmet need (i.e. 5,976 dwellings over the period 2017/18 to 2028/29 as a proportion of the 13,176 dwellings total for those years = 45.36% of the total supply) | 2161.6622
Total WDC Five Year Supply (1/4/24 to 31/3/29) (i.e. 7,200 dwellings over the period 2017/2018 to 2028/29 as a proportion of the 13,176 dwellings total = 54.64% of the total supply) | 2604.4123
Surplus/deficit | -2971.0877
Number of years' supply | 2.3356 | 2011/12: years
Note on A29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The figures provided in light grey reflect the Local Plan requirements and are provided for information only. With the plan becoming over 5 years old, from 2023/24 the Standard Method is now used to calculate the WDC requirement and so supersedes the Local Plan requirement.

## b1) Commitments outline
b1) Commitments - dwellings (outline)
|  |  | Dwellings granted | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40
Hybrid
W/20/2020 | Land at Thickthorn, Kenilworth | Hybrid planning application comprising: Full planning application for 98 dwellings (Class C3) served via two new vehicular / pedestrian / cycle access connections from Leamington Road, pedestrian and cycle access to Thickthorn Close; strategic landscaping and earthworks, surface water drainage and all other ancillary infrastructure and enabling works Outline planning application for demolition of existing buildings and structures; residential development of up to 452 dwellings (Class C3); primary school (Class F.1); employment (Class B2); Class E development; hot food takeaway (sui generis), community centre (Class F.2); strategic landscaping and earthworks, surface water drainage and all other ancillary infrastructure and enabling works with means of site access (excluding internal roads) from the new junction into the detailed parcel of development and access junction off Glasshouse Lane; all other matters (internal access, layout, appearance, scale and landscaping) reserved for subsequent approval. | 452 | 10 | 70 | 80 | 80 | 80 | 320 | 70 | 62
Outline
W/18/0643 | Land at Kings Hill Lane, Stoneleigh | Outline application with access: Development of up to 2,500 dwellings (C3); 4,000 sq.m. of mixed use floorspace (A1, A2, A3, A4, A5, B1, C2, D1 and D2); Primary School; Secondary School, Open Space and Associated Infrastructure | 2500 |  |  |  | 50 | 100 | 150 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 210 | 225 | 225 | 220
W/14/0300 | Land at Asps Farm,bound by Europa Way and Banbury Road , Bishops Tachbrook, Leamington Spa, CV34 6SS | Outline planning application for the erection of up to 900 dwellings a primary school (Use Class D1), a local centre (Use Class A1 to A5 and D1) and a Park and Ride facility for up to 500 spaces (Sui Generis) together with associated infrastructure, landscaping and open space (all matters reserved except access). | 424 | 0 | 90 | 100 | 100 | 100 | 390 | 34
W/20/0617 | Land South of Chesterton Gardens, Leamington Spa | Outline planning application for a residential development of up to 200 dwellings with associated access, landscaping and public open space. (all matters reserved apart from access) | 185 |  | 0 | 20 | 50 | 50 | 120 | 50 | 15
W/19/1030 | Oakley Grove Phase 3, Land off Harbury Lane and Oakley Wood Road, Leamington Spa | Outline planning application for a proposed Primary School and Secondary School with 6th Form, sports pitch provision including flood lights, land for use as a Country Park and a residential development of up to 150 dwellings, with all matters reserved apart from access. | 150 | 0 | 0 | 50 | 50 | 50 | 150
W/22/1038 | Land at Rosswood Farm, Coventry Road, Baginton, Coventry, CV8 3AD | Outline plannning application for the demolition of existing bungalow and erection of up to 63 dwellings (all matters reserved) | 63 |  |  | 10 | 30 | 22 | 62
W/14/0967 | Land North of Gallows Hill, Warwick, CV34 6SJ | Development of up to 425 residential dwellings (Use Class C3), medical centre, community hall, formal and informal green spaces, sports and recreation provision, structural landscaping, new roads, footpaths and cycle ways, site access and ancillary works (outline application including details of access). | 50 | [5 empty] | 0 | 50
W/15/0981 | Land between Myton Road and Europa Way Warwick, | Revised application following planning permission no. W14/1076 to allow for a longer time limit for the commencement of the various phases of development. The development comprises the construction of up to 735 dwellings; a mixed use neighbourhood centre to include retail development (Use Classes A1, A2, A3, & A4 and/or community and health uses (Class D1); safeguarding of land for education use; provision of formal and informal open spaces including sports and recreation provision, childrens and youth play areas and allotments/orchards; strategic landscaping and drainage works including surface water attenuation ponds as part of a sustainable urban drainage system; provision of two vehicular accesses, one off Europa Way and one off Saumur Way; car parking; creation of new footpaths and cycle ways and their connection to adjoining networks; ground remodelling; under grounding of overhead power lines including a new pylon to link to off site overhead lines; and formation of ponds as an ecological mitigation measure to accommodate the translocation of great crested newts. | 37 | [5 empty] | 0 | 37
|  | Total for sites of 10 dwellings or more (net) | 3861 | 10 | 160 | 260 | 360 | 402 | 1192
|  | Total for sites of up to 9 dwellings (net) | 0 | 0 | 0 |  |  |  | 0
|  | Total | 3861 | 10 | 160 | 260 | 360 | 402 | 1192
Thickthorn also appears on tab b2 row 163
Note on D5: Adam James: Total of 548 approved (550+2 demolitions), but 452 approved in outline reflected here
Note on D8: Adam James: Local Plan allocation was 1,800 in the plan period, with up to 4,000 in total. W/18/0643 (granted permission subject to S106) was for up to 2,500 on part of the site. 450 of these dwellings now expected during the plan period.
Note on D9: Adam James: Remaining 424 dwellings with outline approval are represented here. The reserved matters permission W/19/0229 (65 dwellings) is not expected to be implemented.
Note on D10: Sarah Cleverley: 200 allocated in LP but RM application for 185.
Note on D12: Adam James: 63 dwellings approved but 62 net additional dwellings accounting for the demolition of the existing bungalow
Note on D13: Sarah Cleverley: Of the 425 dwellings approved, 375 have reserved matters permission under W/19/0346; the remaining 50 are here. Due to length of time since Outline Permission was granted a new application may be needed to bring these forward. Therefore removed from the plan period.
Note on D14: Michael Brown: Of the 735 dwellings approved, 698 have reserved matters permission under W/18/1442, W/18/1832, W/19/1445 and W/20/0232; the remaining 37 are here. Due to the length of time since Outline permission was granted a new applicaiotn may be needed to bring these forward. Therefore removed from the current plan period.

## b2) Commitments full
b2) Commitments - dwellings (full permission)
|  |  | Dwellings granted | Under construction | Completed | Not started | Remaining (UC + NS) | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 |  | Total
Full
W/18/2313 | Land South of Gallows Hill and West of Europa Way Warwick CV34 6SP | Submission of Reserved Matters (Layout, Scale, Appearance and Landscaping) pursuant to condition 1 of Outline Planning Permission W/14/0681 (as amended by W/17/0894) for 450 residential units with associated car and cycle parking provision, open space and public realm, childrens play space, landscaping, revised access from spine road and associated infrastructure works | 450 | 87 | 136 | 227 | 314 | 87 | 35 | 85 | 85 | 22 |  | 314
W/21/1811 | Land On The East Side Of, Glasshouse Lane, Kenilworth | Demolition of existing farmhouse and agricultural buildings and outline planning application for residential development of up to 620 dwellings (Use Class C3), new primary school (Use Class F.1) including means of access into site (not internal roads), parking and associated works, with all other matters (relating to appearance, landscaping, scale and layout) reserved | 620 | 63 | 60 | 496 | 559 | 113 | 116 | 120 | 120 | 90 |  | 559
W/19/0346 | Land North of Gallows Hill, Warwick, CV34 6SJ | Reserved Matters application for the development of 375 dwellings, green spaces, road, footways and ancillary works in pursuance of outline planning permission W/14/0967 (outline for up to 425 Residential dwellings, varied by W/18/1619) | 375 | 43 | 332 | 0 | 43 | 43 | [5 empty] | 43
W/21/1280 | Land South of Westwood Heath Road, Burton Green, Coventry | Reserved Matters application pursuant to condit | 296 | 0 | 0 | 296 | 296 | 41 | 78 | 98 | 72 | 7 |  | 296
W/21/0955 | Land at the Asps, Bound by Europa Way (A452) to the east and Banbury Road (A425) to the west, Leamington Spa, CV34 6SS | Reserved Matters application pursuant to condit | 271 | 79 | 55 | 137 | 216 | 56 | 60 | 75 | 25 |  |  | 216
W/20/0232 | Land between Myton Road and Europa Way, (Parcel 4) Warwick | Application for Reserved Matters pursuant to condition 1 of planning permission ref:W/15/0981 for details of appearance, layout and scale of 235 dwellings including access road, public open space and ancillary works | 235 | 76 | 142 | 17 | 93 | 50 | 38 | 5 |  |  |  | 93
W/21/0930 | Land at the Asps, Bound by Europa Way (A452) to the east and Banbury Road (A425) to the west, Leamington Spa, CV34 6SS | Reserved Matters application pursuant to condit | 205 | 88 | 41 | 76 | 164 | 91 | 59 | 12 |  | 2 |  | 164
W/21/0577 | Land South of Gallows Hill / Banbury Hill Warwick, CV34 6RN | Application for approval of reserved matters in pu | 180 | 0 | 0 | 180 | 180 |  |  | 30 | 50 | 50 |  | 130
W/19/0933 | Land On The North Side Of, Birmingham Road, Hatton | Full Planning Application - 150 Dwellings (Class C3); New Vehicular Access from Birmingham Road; New Temporary Vehicular Access for Sales and Construction from Birmingham Road; & Associated Works | 150 | 52 | 15 | 83 | 135 | 50 | 55 | 30 |  |  |  | 135
W/21/0427 | Land to the South of Westwood Heath Road, Burton Green,Coventry | Variation of conditions 4 (approved plans) and 26 (approved plans in relation to highway works) of planning permission W/17/2357 (Hybrid planning application for the erection of up to 425 dwellings [including detailed first phase of 129 dwellings with remainder of the site being outline including details of access], convenience store, open space, infrastructure provision and means of access onto Westwood Heath Road / agricultural access onto Bockendon Lane) to allow changes to the house types and the layout of the secondary roads within the detailed phase (129 dwellings) of the site. There are no material changes proposed to the approved development parcels within Phase 1. | 129 | 14 | 115 | 0 | 14 | 14 | [5 empty] | 14
W/20/2089 | Land On East Side Of, Warwick Road, Kenilworth, CV8 1FE | Provision of 4 additional dwellings on existing development site (reserved matters approval for 125 under W/19/0784) through the substitution of 3no. 5-bed dwellings with 7no. 3-bed dwellings within the existing site layout. | 125 | 3 | 122 | 0 | 3 | 3 | [5 empty] | 3
W/20/0760 | WCC County Store Depot and Former Ridgeway School , Montague Road, Warwick, CV34 5LW | Application for full planning permission for the demolition of existing buildings and construction of 121 dwellings with associated internal roads, footways, cycleways and retained access for ambulance station. | 121 | 30 | 81 | 10 | 40 | 40 | [5 empty] | 40
W/19/1940 | Kings High School for Girls, Chapel Street, Warwick, CV34 4HJ | Redevelopment of former King's High School site consisting of main school site, Priory Building, St Nicholas Building and Numbers 2 and 10-14 Chapel Street. Development to include the demolition of gymnasium building, sixth form building, language building, Priory Building and modern elements attached to the Listed Buildings together with alterations to the external appearance of retained non-Listed Buildings. Erection of new apartment buildings and town houses together with the conversion of retained buildings to create a total of 118no. residential units in a mixture of houses, apartments and duplexes. Creation of underground car and cycle parking together with hard and soft landscaping and other associated works. | 113 | 0 | 0 | 113 | 113 |  |  |  | 10 | 35 |  | 45
W/21/0550 | Land at Glasshouse Lane, Kenilworth | Reserved Matters approval for 99 no. dwellings, | 99 | 38 | 31 | 30 | 68 | 55 | 13 |  |  |  |  | 68
W/20/0808 | Land north of Rosswood Farm, Coventry Road, Baginton, Coventry, CV8 3AD | Full application for the proposed development of 56 no. affordable dwellinghouses, consisting of mixed tenure of Social Rent and Shared Ownership on land adjacent to Coventry Road, Baginton. | 56 | 0 | 0 | 56 | 56 |  | 56 |  |  |  |  | 56
W/18/0554 | Waverley Riding School, Coventry Road, Cubbington, Leamington Spa, CV32 7UJ | Demolition and redevelopment of existing equestrian centre to provide 16 no. dwellings (Class C3); widening and improvement to existing vehicular access and road off Coventry Road; and provision of associated parking, landscaping and surface water attenuation | 17 | 17 | 0 | 0 | 17 | 17 | [5 empty] | 17
W/20/1240 | 18-20 Parade, Leamington Spa, CV32 4DW | Change of use from existing offices on all floors at 18 Parade and first, second and third floors only at 20 Parade to create 10no. self-contained apartments. | 10 | 10 | 0 | 0 | 10 | 10 | [5 empty] | 10
W/21/0939 | The Old Leper Hospital, St Michaels Chapel, The Master's house and adjacent land,Saltisford, CV34 4TT | Full planning application for the (i) change of use | 10 | 0 | 0 | 10 | 10 |  |  | 2 | 8 |  |  | 10
W/22/2000 | 149 - 151 Warwick Road, Kenilworth, CV8 1HY | Demolition of existing hotel and 151 Warwick R | 9 | 0 | 0 | 9 | 9
W/20/0312 | 54 Kenilworth Road, Leamington Spa, CV32 6JW | Proposed conversion from single dwelling to form 5no. 1 bedroom and 3no. 2 bedroom apartments. Demolition of existing single storey side extension and erection of replacement single storey side extension (re-submission of previously withdrawn W/19/1562). | 8 | 9 | -1 | 0 | 9
W/22/0463 | Land adjacent, 9 Clarendon Place, Leamington Spa, CV32 5QL | Demolition of cadet hut and storage building; ere | 8 | 0 | 0 | 8 | 8
W/22/0830 | 90 Nelson Lane, Warwick, CV34 5JB | Demolition of existing buildings, erection of 8no. | 8 | 0 | 0 | 8 | 8
W/22/1407 | Glebe Hotel, Church Street, Barford, Warwick, CV35 8BS | Redevelopment of former Glebe hotel, including | 8 | 0 | 0 | 8 | 8
W/22/1546 | 16 Cross Street, Leamington Spa, CV32 4PX | Demolition of existing building and erection of an | 8 | 8 | 0 | 0 | 8
W/08/1438 | 16 Wise Street/5 & 6 Wise Terrace, Leamington Spa, CV31 3AP | Construction of 7 apartments and 8 parking spaces | 7 | 0 | 0 | 7 | 7
W/23/1084 | 17 Beverley Road, Leamington Spa, CV32 6PH | Demolition of existing dwelling and construction | 7 | 0 | 0 | 7 | 7
W/21/0965 | Land East of Turpin Court, Leamington Spa, CV31 3JU | Variation of condition 2 (plan numbers) of permission W/20/0158 (erection of 6 dwellings), to allow for design changes to plots 3, 4, 5 and 6 to provide single terrace of 4 properties; alterations to roofs of properties. | 6 | 0 | 0 | 6 | 6
W/22/0735 | 91-93 Regent Street, Leamington Spa, CV32 4NT | Conversion of upper floors to create 2no. 1 bed a | 6 | 6 | 0 | 0 | 6
W/22/1465 | Agricultural Building, Land off Pit Hill, Bubbenhall | Application for Prior Approval under Schedule 2, | 5 | 0 | 0 | 5 | 5
W/23/1315 | Crackley Farm, Crackley Lane, Kenilworth, CV8 2JS | Application for Prior Approval for the proposed c | 5 | 0 | 0 | 5 | 5
W/23/1530 | Agricultural Buildings 1 and 2 Sawpit Close Farm, Ryton Road, Bubbenhall, Coventry, CV8 3BH | Prior Approval application for proposed conversio | 5 | 0 | 0 | 5 | 5
W/08/0878 | 14 Wise Street, Leamington Spa, CV31 3AP | Demolition of existing commercial premises and erection of a three storey (and basement) building to provide 4 no apartments with 4 no parking spaces | 4 | 0 | 0 | 4 | 4
W/18/0958 | Shop and Premises, 170 Emscote Road, Warwick, CV34 5QN | Proposed change of use of takeaway shop (A5) to ground floor and internal alterations to provide 5 flats (C3 use) (Resubmission of W/18/0659). | 4 | 4 | 0 | 0 | 4
W/20/0719 | 2,5,6 & 7 Bertie Terrace, Leamington Spa, CV32 5BL | Conversion of existing basements to number 2, 5, 6 and 7 Bertie Terrace to form 4 new residential units (C3 Use), including associated landscaping works to the rear to provide new private amenity space. | 4 | 4 | 0 | 0 | 4
W/20/1538 | Flat, 35-37 Parade, Leamington Spa, CV32 4BL | Change of use and conversion of upper floors int | 4 | 0 | 0 | 4 | 4
W/21/1750 | Oakley Wood Barns, Banbury Road, Bishops Tachbrook, Leamington Spa, CV33 9QJ | Conversion of a redundant agricultural building in | 4 | 4 | 0 | 0 | 4
W/14/1479 | Bridge Dental Practice, Court Street, Leamington Spa, CV31 2BB | Additional storey extension and internal alterations to provide 3 flats (1 x 1 bed and 2 x 2 bed) | 3 | 0 | 0 | 3 | 3
W/15/1993 | 63 Bedford Street, Leamington Spa, CV32 5DN | Change of use of ground floor from a hot food takeaway (Use Class A5) to offices (Use Class B1a); change of use of first floor from offices and erection of second floor extension to create 3 no. flats (Use Class C3); and external alterations | 3 | 0 | 0 | 3 | 3
W/17/2328 | 9-11 Clemens Street, Leamington Spa, CV31 2DW | Change of use of ground floor storage area and first floor and erection of second floor to provide 3no. flats | 3 | 0 | 0 | 3 | 3
W/20/1662 | 168 Emscote Road, Warwick, CV34 5QN | Change of use and conversion from 5 bed HMO (Use Class C4) to 3no. 1 bed flats (Use Class C3), to include raising of the ridge height, erection of second floor rear extension, front and rear rooflights and dormer window and rear access steps. | 3 | 0 | 0 | 3 | 3
W/21/0396 | Flat, 25 High Street, Leamington Spa, CV31 1LN | Change of use and conversion from 6 bed House in Multiple Occupation (Use Class C4) to 3no. 1 bedroom flats | 3 | 3 | 0 | 0 | 3
W/21/0743 | 3 Euston Place, Leamington Spa, CV32 4LN | Change of use and conversion of upper floors fro | 3 | 0 | 0 | 3 | 3
W/21/0721 | Brook Farm, Myton Road, Warwick, CV34 6SB | Erection of three detached dwellings; and associated alterations and single-storey extension to Brook Farm House | 3 | 0 | 0 | 3 | 3
W/21/1420 | 7 Clarendon Place, Leamington Spa, CV32 5QL | Proposed erection of an apartment block to provide 3no. two bedroom apartments, with associated parking and storage (Re-submission of approved planning application under refs: W/16/1824 and W/18/2260) | 3 | 0 | 0 | 3 | 3
W/21/2131 | 138 Rugby Road, Leamington Spa, CV32 6DS | Construction of 3no. apartments and associated | 3 | 3 | 0 | 0 | 3
W/23/0493 | The Lyons Farm House, Rowington Green, Rowington, Warwick, CV35 7DB | Redevelopment of farm building to provide three | 3 | 0 | 0 | 3 | 3
W/05/1446 | Park Farm Barns, Stareton Lane, Stoneleigh, Kenilworth, CV8 2LL | Conversion of barns to 3 live-work units | 3 | 0 | 1 | 2 | 2
W/17/2084 | Kites Nest Farm, Kites Nest Lane, Beausale, Warwick, CV35 7PB | Proposed conversion of barns and outbuildings to provide three dwellings | 3 | 1 | 1 | 1 | 2
W/94/0208 | VILLAGE FARM, OFFCHURCH. | Part demolition, conversion and extension of barns to provide 3 dwellings and garages; erection of garage; conversion of outbuilding to form garaging; erection of a screenwall; retention of part of outbuilding within curtilage of house 2. | 3 | 0 | 0 | 3 | 3
W/16/1725 | Horsley House Farm, Norton Curlieu Lane, Norton Lindsey, Warwick, CV35 8RD | i) residential conversion of former threshing barn; ii) extensive site clearance and erection of a new barn-style dwelling, and iii) partial demolition, extension, alteration and restoration of Grade II listed farmhouse; plus conversion of barn to form holiday-let, erection of two timber stables and the upgrading of permissive public footpath through the site. | 2 | 2 | 0 | 0 | 2
W/18/2312 | Priors Club, Tower Street, Leamington Spa, CV31 2DR | The demolition of existing social club and erection of two & three storey cafe and bar with ancillary managers flat and staff accommodation. | 2 | 0 | 0 | 2 | 2
W/18/2335 | Lodge Farm House, Westwood Heath Road, Coventry, CV4 8AA | Erection of 2no. dwellings. | 2 | 2 | 0 | 0 | 2
W/19/0751 | Tapster Manor, Tapster Lane, Lapworth, Solihull, B94 5PG | Resubmission - proposed conversion of redundant stables to form one x 2bedroom single storey dwelling with parking and amenity space (amended scheme - two units reduced to one unit to provide appropriate space for bat mitigation loft) | 2 | 0 | 0 | 2 | 2
W/20/1415 | 62 Brunswick Street, Leamington Spa, CV31 2EG | Proposed second floor extension to form 2no new flats, extension to HMO on first floor to provide new living area, extension to shop on ground floor at front and increase in size of basement. | 2 | 0 | 0 | 2 | 2
W/20/1538 | Flat, 35-37 Parade, Leamington Spa, CV32 4BL | Change of use and conversion of upper floors into 2no. flats | 2 | 0 | 0 | 2 | 2
W/21/0410 | 62 Leam Terrace, Leamington Spa, CV31 1BQ | Erection of 2no. 1 bed maisonette flats to land r | 2 | 0 | 0 | 2 | 2
W/21/0527 | Four Brothers Farm, Five Ways Road, Shrewley, Warwick, CV35 7JB | Demolition of agricultural building and erection o | 2 | 2 | 0 | 0 | 2
W/21/0538 | 60 Regent Street, Leamington Spa, CV32 5EG | Change of use of first and second floors to provi | 2 | 0 | 0 | 2 | 2
W/21/1313 | Baginton School Site, Church Road, Baginton, CV8 3AR | Erection of 2no new dwellings incorporating associated landscaping and proposal of a new peace garden | 2 | 0 | 1 | 1 | 1
W/22/0159 | Montpelier House, Southbank Road, Kenilworth, CV8 1LA | Creation of 2no. additional 1-bed flats through in | 2 | 2 | 0 | 0 | 2
W/22/0175 | 1 Park Road, Kenilworth, CV8 2GF | Proposed change of use from five bedroom licen | 2 | 0 | 0 | 2 | 2
W/22/0305 | 3 Gulistan Road, Leamington Spa, CV32 5LU | Erection of a pair of semi-detached two bedroom | 2 | 2 | 0 | 0 | 2
W/22/0737 | 41 Avenue Road, Leamington Spa, CV31 3PF | Proposed reconfiguration of flat 1 to create 2no. | 2 | 0 | 0 | 2 | 2
W/22/1036 | Kenilworth Lodge, Leamington Road, Kenilworth, CV8 2AA | Erection of 2no. dwelling houses on garden to th | 2 | 0 | 0 | 2 | 2
W/22/1328 | Bridge Works, Farmer Ward Road, Kenilworth, CV8 2DH | Erection of single storey side extension to creat | 2 | 0 | 0 | 2 | 2
W/23/1394 | 64-66 Market Place, Warwick | Conversion of existing offices into 2no. one bedr | 2 | 0 | 0 | 2 | 2
W/23/1425 | 6 Lillington Avenue, Leamington Spa, CV32 5UJ | Proposed works comprising three storey rear ex | 2 | 0 | 0 | 2 | 2
W/23/1680 | Shop and Premises, 5 Old Milverton Road, Milverton, Leamington Spa, CV32 6AY | Change of use from ground floor shop (Use Clas | 2 | 0 | 0 | 2 | 2
W/21/1402/LB | 102 Parade, Leamington Spa, CV32 4AQ | Internal alterations to facilitate conversion of upper floors to flats | 2 | 2 | 0 | 0 | 2
W/02/1636 | HILL FARM, OFFCHURCH ROAD, CUBBINGTON. | Variation of Condition No. 1 of P.P. W971539 to extend 5 year time limit for the conversion of barns to provide 3 dwelling units and 7 garages. | 1 | 1 | 0 | 0 | 1
W/15/1230 | Land off, Charles Street, Warwick, CV34 5LQ | Erection of one bedroom dwelling. | 1 | 1 | 0 | 0 | 1
W/15/1635 | 56 Southam Road, Radford Semele, Leamington Spa, CV31 1TA | Erection of 1no. dwellinghouse and alteration to existing access | 1 | 1 | 0 | 0 | 1
W/15/1683 | Land to Rear of Avon Court, School Lane, Kenilworth | Proposed chalet style house, land to rear of Avon Court School Lane Kenilworth (site of existing garages) | 1 | 1 | 0 | 0 | 1
W/16/2209 | 4 Windsor Street, Leamington Spa, CV32 5EB | Erection of a two and three storey dwelling after demolition of existing building | 1 | 0 | 0 | 1 | 1
W/17/1584 | 1 Castle Hill, Kenilworth, CV8 1NB | Proposed conversion of existing lower ground floor to self contained one bedroomed apartment. | 1 | 1 | 0 | 0 | 1
W/18/1086 | 1 Masefield Avenue, Warwick, CV34 6JU | Erection of 2 bed dwellling house | 1 | 1 | 0 | 0 | 1
W/18/1292 | 1 Nursery Lane, Leamington Spa, CV31 2PW | Proposed erection of a two bedroom dwelling | 1 | 1 | 0 | 0 | 1
W/18/1419 | 57-59 Regent Street, Leamington Spa, CV32 5EE | Proposed subdivision of the ground floor retail un | 1 | 1 | 0 | 0 | 1
W/18/1448 | 2 & 3 Birmingham Road, Stoneleigh, Coventry, CV8 3DD | Proposed sub-division of single dwelling to form | 1 | 1 | 0 | 0 | 1
W/18/1779 | Shop and Premises, 170 Emscote Road, Warwick, CV34 5QN | Proposed alterations and rear extension form a second floor flat. | 1 | 1 | 0 | 0 | 1
W/18/2148 | The Mill, Mill Lane, Little Shrewley, Shrewley, Warwick, CV35 7HN | Amendments to planning permission ref: W/18/0067 (Conversion (with minor extensions and alterations) of craft workshops building to 1no. house, including ancillary business use). | 1 | 1 | 0 | 0 | 1
W/18/2282 | Barn Adjacent to Wappenbury Hall, Main Street, Wappenbury, Leamington Spa, CV33 9DW | Application under Class Q(a) and (b) of the GPDO for the conversion of existing barn into a single dwelling including external works to facilitate the use | 1 | 1 | 0 | 0 | 1
W/19/0362 | The Maze, Hall Drive, Baginton, Coventry, CV8 3AF | Proposed new build property on the land adjacent to The Maze. | 1 | 1 | 0 | 0 | 1
W/19/1482 | 122 Rouncil Lane, Kenilworth, CV8 1FP | Demolition of two storey, four bedroom dwelling and erection of 2no three storey, five bedroom dwellings. | 1 | 2 | -1 | 0 | 2
W/19/2080 | Barnwell Farm, Harbury Lane, Bishops Tachbrook, Leamington Spa, CV33 9QB | Construction of a new dwelling house to be occupied by an agricultural worker to replace existing mobile home. | 1 | 1 | 0 | 0 | 1
W/20/0749 | 58 Regent Street, Leamington Spa, CV32 5EG | Change of use of first and second floors from storage in acconection with the ground floor shop to a 1no. self contained 2 bed flat. Associated works include a new shopfront to provide independent flat entrance off Regent Street, replacement second floor rear window and insertion of first floor window to the rear elevation. | 1 | 0 | 0 | 1 | 1
W/20/1380 | Land at Crewe lane, Crewe Lane, Kenilworth | Erection of 1no. dwelling with associated access onto Crewe Lane | 1 | 1 | 0 | 0 | 1
W/20/1828 | Clattylands Barn, Haseley Knob, Haseley, Warwick, CV35 7NJ | Conversion and change of use of existing barn and stables into 1no. dwellinghouse with associated boundary treatements and hardstandings | 1 | 0 | 0 | 1 | 1
W/20/1847 | Rosedale, Main Street, Eathorpe, Leamington Spa, CV33 9DE | Erection of 1no. dwelling and associated vehicular access. | 1 | 1 | 0 | 0 | 1
W/20/2161 | Land Fronting Red Lane, Burton Green, Kenilworth, CV8 1PB | Erection of single dwelling and associated garage | 1 | 0 | 0 | 1 | 1
W/21/0446 | Shrewley Gate Nursery, Old Warwick Road, Shrewley, Warwick, CV35 7AX | Demolition of existing buildings and structures and erection of a single dwelling and associated landscaping. | 1 | 0 | 0 | 1 | 1
W/21/0647 | The Rye House, Catesby Lane, Lapworth, Solihull, B94 5QY | Conversion of stable building to 1no. dwelling (amendment to approved design under W/18/1820) | 1 | 0 | 0 | 1 | 1
W/21/0708 | Barn 6 -Stanks Farm,Old Budbrooke Road, Budbrooke, Warwick, CV35 8RH | Conversion of Barn 6 to a dwelling | 1 | 0 | 0 | 1 | 1
W/21/0835 | Finwood Hill Farm, Mill Lane, Rowington, Warwick, B95 5HH | Application for the conversion of rural building into a residential dwelling. | 1 | 0 | 0 | 1 | 1
W/21/1071 | The Elms, 75 Chessetts Wood Road, Lapworth, Solihull, B94 6EL | Variation of Condition 2 (approved plans) of planning permission ref: W/19/1389 (Erection of one detached dwelling and integral garage, with use of existing access) to seek approval for an amendment to the site boundary and design of the dwelling. Re-registered with HM Land Registry on 22nd December 2021 due to technical issues. | 1 | 1 | 0 | 0 | 1
W/21/1239 | 1 Crackley Cottages, Coventry Road, Kenilworth, CV8 2FG | Subdivision of existing dwelling to form 2no. dwellings, erection of first floor rear extension to each new dwelling and erection of conservatory to dwelling No.2 | 1 | 0 | 0 | 1 | 1
W/21/1255 | Land off Bushwood Lane, Lapworth, B94 5PJ | Change of use of building to holiday accommod | 1 | 1 | 0 | 0 | 1
W/21/1276 | 2 Church Lane, Cubbington, Leamington Spa, CV32 7JT | Demolition of existing cottage ground floor side | 1 | 1 | 0 | 0 | 1
W/21/1392 | Hillside House, 50 Bakers Lane, Knowle, Solihull, B93 8PW | Conversion of agricultural building, adjacent stable and garage to a single dwelling (Use Class C3), following Class Q approval for conversion of agricultural building (W/21/0098) | 1 | 0 | 0 | 1 | 1
W/21/1493 | 1 Rock Cottages, Warwick Road, Leek Wootton, Warwick, CV35 7RB | Demolition of existing garage & erection of 1no. | 1 | 0 | 0 | 1 | 1
W/21/1994 | Shepherds Fold, Finwood Road, Rowington, Warwick, CV35 7DF | Conversion of redundant barn to dwelling | 1 | 0 | 0 | 1 | 1
W/21/2144 | Chapel Hill Farm, Oakley Wood Road, Bishops Tachbrook, Leamington Spa, CV33 9QE | Conversion of rural building to create single dwe | 1 | 0 | 0 | 1 | 1
W/21/2232 | Lansdowne Hotel, 87-89 Clarendon Street, Leamington Spa, CV32 4PF | Change of Use of No.89 Clarendon Street from a | 1 | 1 | 0 | 0 | 1
W/22/0214 | Austin Guest House, 96 Emscote Road, Warwick, CV34 5QJ | Change of use from Guest House (Use Class C | 1 | 1 | 0 | 0 | 1
W/22/0270 | Poundley End, Rookery Lane, Lowsonford, Solihull, B95 5EP | Application for Prior Approval under Schedule 2, Part 3, Class Q (a) and (b) for proposed change of use of agricultural building to a dwelling house (Use Class C3) and associated external alterations | 1 | 0 | 0 | 1 | 1
W/22/0341 | Valley Farm, Valley Lane, Lapworth, Solihull, B94 6HB | Application for Prior Approval under Part 3, Clas | 1 | 1 | 0 | 0 | 1
W/22/0367 | Clinton House, Old Warwick Road, Rowington, Warwick, CV35 7BT | Erection of single storey dwelling | 1 | 0 | 0 | 1 | 1
W/22/0376 | 12 Maple Grove, Warwick, CV34 5SS | Proposed erection of three bedroom dwelling | 1 | 1 | 0 | 0 | 1
W/22/0841 | 9 Jury Street, Warwick, CV34 4EH | Alterations and extensions to existing building t | 1 | 1 | 0 | 0 | 1
W/22/0890 | 28 Clarendon Square, Leamington Spa, CV32 5QX | Conversion of basement to a 2 bed apartment | 1 | 1 | 0 | 0 | 1
W/22/1124 | 18 Parade, Leamington Spa, CV32 4DW | Proposed conversion of existing basement to 1n | 1 | 1 | 0 | 0 | 1
W/22/1393 | 3 Lewis Road, Radford Semele, Leamington Spa, CV31 1UB | Erection of 1no. bungalow | 1 | 0 | 0 | 1 | 1
W/22/1788 | Stables, High Paddock, Back Lane, Rowington, Solihull, CV35 7BD | Conversion of existing rural building to form a dw | 1 | 0 | 0 | 1 | 1
W/22/1886 | The Rye House, Catesby Lane, Lapworth, Solihull, B94 5QY | Demolition of former equestrian building and ere | 1 | 0 | 0 | 1 | 1
W/22/1932 | 2 Highland Road, Kenilworth, CV8 2ET | Demolition of existing dwelling and erection of 2 | 1 | 0 | 0 | 1 | 1
W/22/1959 | Hampton Hill Farm, Littleworth Road, Budbrooke, Warwick, CV35 8HB | Conversion of building to a dwellinghouse and er | 1 | 1 | 0 | 0 | 1
W/23/0024 | Oakfield, Old Warwick Road, Lapworth, Solihull, B94 6JZ | Demolition of existing outbuilding and erection o | 1 | 1 | 0 | 0 | 1
W/23/0060 | 99 Upper Holly Walk, Leamington Spa, CV32 4JU | Erection of a second storey rear extension and | 1 | 0 | 0 | 1 | 1
W/23/0167 | Lowsonford Barn, Lapworth Street, Bushwood, Lowsonford, Henley-in-Arden, B95 5HJ | Change of use of B1 (a) Office to a dwelling (Us | 1 | 0 | 0 | 1 | 1
W/23/0178 | Middle Farm Barn, Oakley Wood Road, Bishops Tachbrook, Leamington Spa, CV33 9RT | Prior Approval for the change of use of an agricu | 1 | 0 | 0 | 1 | 1
W/23/0239 | Land at Field Close, Leamington Spa | Erection of 1no. dwelling | 1 | 1 | 0 | 0 | 1
W/23/0303 | Offa House, Village Street, Offchurch, Leamington Spa, CV33 9AS | Restoration of Offa House including demolition o | 1 | 1 | 0 | 0 | 1
W/23/0326 | Lapworth House, Wharf Lane, Lapworth, Solihull, B94 5QH | Change of use and conversion of brick built barn | 1 | 0 | 0 | 1 | 1
W/23/0523 | Cherry Apple Cottage, Warwick Road, Leek Wootton, Warwick, CV35 7RB | Erection of 1no. Four Bedroom Dwelling House | 1 | 1 | 0 | 0 | 1
W/23/0723 | Barn, Middle Farm, Oakley Wood Road, Bishops Tachbrook, CV33 9RT | Change of use and conversion of agricultural bui | 1 | 0 | 0 | 1 | 1
W/23/0788 | Lapworth Grange, Spring Lane, Lapworth, Solihull, B94 5NT | Conversion of former Coach House to create 1no | 1 | 0 | 0 | 1 | 1
W/23/0789 | Lapworth Grange, Spring Lane, Lapworth, Solihull, B94 5NT | Conversion of brick barn to create a single dwell | 1 | 0 | 0 | 1 | 1
W/23/0915 | 16 Watersfield Gardens, Leamington Spa, CV31 1NT | Erection of 1no. dwelling | 1 | 0 | 0 | 1 | 1
W/23/0954 | 7 Kenilworth Road, Cubbington, Leamington Spa, CV32 7TN | Erection of detached one-and-a-half storey dwel | 1 | 0 | 0 | 1 | 1
W/23/0981 | Inchford Brook House, Kites Nest Lane, Beausale, Warwick, CV35 7PB | Conversion of former stables and livestock build | 1 | 0 | 0 | 1 | 1
W/23/1149 | 163 Cromwell Lane, Burton Green, Kenilworth, CV4 8AN | Outline planning application (with all matters res | 1 | 0 | 0 | 1 | 1
W/23/1185 | Land to the North of, Bakers Lane, Knowle, Solihull | Proposed dwelling in lieu of extant Class Q Prio | 1 | 1 | 0 | 0 | 1
W/23/1207 | 151 Warwick Road, Kenilworth, CV8 1HY | Demolition of existing dwelling at No.151 Warwi | 1 | 0 | 0 | 1 | 1
W/21/0924 | Pear Tree Cottage, Stoneleigh Road, Blackdown, Leamington Spa, CV32 6QR | Demolition of existing dwelling and erection of a | 0 | 1 | -1 | 0 | 1
W/21/1855 | Lantern House, Chessetts Wood Road, Lapworth, Solihull, B94 6EP | Variation of Condition 2 (approved plans) of plan | 0 | 1 | -1 | 0 | 1
W/18/0921 | Ley End Farm, School Lane, Beausale, Warwick, CV35 7NW | Demolition of existing farmhouse, domestic outbuildings and agricultural buildings and erection of replacement farmhouse, new garaging and new farmyard access | 0 | 0 | 1 | -1 | -1
W/22/0215 | 71 Inchbrook Road, Kenilworth, CV8 2EW | Demolition of existing dwelling and proposed ere | 0 | 1 | -1 | 0 | 1
W/22/0304 | Bericote House, Stoneleigh Road, Blackdown, Leamington Spa, CV32 6QR | Erection of replacement dwelling and associated | 0 | 1 | -1 | 0 | 1
W/22/0377 | 162 Millbank, Warwick, CV34 5TJ | Proposed erection of replacement two storey dw | 0 | 1 | -1 | 0 | 1
W/22/1141 | Little Fieldgate, 55 Fieldgate Lane, Kenilworth, CV8 1BT | Demolition of existing bungalow and garage and | 0 | 1 | -1 | 0 | 1
W/22/1910 | Pine Cottage, Rising Lane, Lapworth, Solihull, B94 6JB | Demolition of existing dwelling and erection of a | 0 | 1 | -1 | 0 | 1
W/22/1957 | 16 Cloister Way, Leamington Spa, CV32 6QE | Demolition of an existing detached dwelling and | 0 | 1 | -1 | 0 | 1
W/23/0162 | Wyken Field, High Cross Lane, Rowington, Warwick, CV35 7BE | Application for approval of Reserved Matters (ap | 0 | 1 | -1 | 0 | 1
W/23/0177 | 13 Kenilworth Road, Cubbington, Leamington Spa, CV32 7TN | Erection of replacement dwelling | 0 | 1 | -1 | 0 | 1
W/22/0199 | 481 Tachbrook Road, Whitnash, Leamington Spa, CV31 3DQ | Conversion of Nos 481 and 481A to single dwelling with front and rear extensions and hip to gable roof alteration. Resubmission of W/21/0254 | -1 | 1 | -2 | 0 | 1
W/21/0435 | Flat, Grist Mill, Chesterton Drive, Leamington Spa, CV31 1YJ | Change of use from residential dwelling (Use Class C3) to 5 bed house in multiple occupation (Use Class C4). (Resubmission of W/20/0987) | -1 | 0 | 0 | -1 | -1
W/21/0920 | 52 Bury Road, Leamington Spa, CV31 3HN | Application for the change of use of a dwelling (use class C3) to a 3 bed House in Multiple Occupation (HMO) (use class C4). | -1 | 0 | 0 | -1 | -1
W/22/0001 | 43 Buckley Road, Lillington, Leamington Spa, CV32 7QG | Change of use from 3 bedroom dwellinghouse (U | -1 | 0 | 0 | -1 | -1
W/22/0564 | 58A Clemens Street, Leamington Spa, CV31 2DN | Change of use from 3 bed dwellinghouse (Use C | -1 | 0 | 0 | -1 | -1
W/23/0084 | Flat 2, 10 Dale Street, Leamington Spa, CV32 5HJ | Change of use from 2 bedroom flat (C3) to 3 bed | -1 | 0 | 0 | -1 | -1
W/23/0760 | 38 Cobden Avenue, Leamington Spa, CV31 1YF | Change of use from 4 bed dwellinghouse (Use C | -1 | 0 | 0 | -1 | -1
W/23/0945 | 11 Hornbeam Grove, Sydenham, Leamington Spa, CV31 1QX | Change of use from Use Class C3 (residential d | -1 | 0 | 0 | -1 | -1
W/23/1231 | 15 Beaufort Avenue, Cubbington, Leamington Spa, CV32 7TA | Proposed change of use from existing use as a | -1 | 0 | 0 | -1 | -1
W/23/1665 | 218 Emscote Road, Warwick, CV34 5QT | Application for Lawful Development Certificate fo | -1 | -1 | 0 | 0 | -1
W/19/1205 | Dalehouse Farm, Dalehouse Lane, Kenilworth, CV8 2JZ | Change of use from dwelling (Use Class C3) to residential training centre (Use Class C2) | -2 | 0 | 0 | -2 | -2
W/19/1911 | 47 Cubbington Road, Lillington, Leamington Spa, CV32 7AA | Demolition of numbers 43-49 Cubbington Road, Leamington Spa and the erection of 1no. two-storey replacement dwelling together with the demolition of an existing garage block and the erection of a two-storey garage block. | -3 | 1 | -4 | 0 | 1
Hybrid
W/20/2020 | Land at Thickthorn, Kenilworth | Hybrid planning application comprising: Full planning application for 98 dwellings (Class C3) served via two new vehicular / pedestrian / cycle access connections from Leamington Road, pedestrian and cycle access to Thickthorn Close; strategic landscaping and earthworks, surface water drainage and all other ancillary infrastructure and enabling works Outline planning application for demolition of existing buildings and structures; residential development of up to 452 dwellings (Class C3); primary school (Class F.1); employment (Class B2); Class E development; hot food takeaway (sui generis), community centre (Class F.2); strategic landscaping and earthworks, surface water drainage and all other ancillary infrastructure and enabling works with means of site access (excluding internal roads) from the new junction into the detailed parcel of development and access junction off Glasshouse Lane; all other matters (internal access, layout, appearance, scale and landscaping) reserved for subsequent approval. | 98 | 54 | 38 | 6 | 60 | 22 | 38 |  |  |  |  | 60
[6 empty] | Total for sites of 10 dwellings or more (net) | 2391 | 692 | 548 | 457 | 370 | 206 | 0 | 2273
[6 empty] | Total for sites of up to 9 dwellings (net) | 252 | 84 | 84 | 84 |  |  |  | 252
[6 empty] | Total | 2643 | 776 | 632 | 541 | 370 | 206 | 0 | 2525
Note on D6: Michael Brown: 620 new dwellings and 1 demolition.
Note on D8: Sarah Cleverley: 236 from Crest Nicholson and 70 from William Davis Homes who have now purchased a portion of the site.
Note on D17: Sarah Cleverley: Application is for 118. However, separate application has been received for one section of the permission (W/24/0537) for 4 dwellings on Site D which had 5 dwellings in the original permission here therefore removing from here.
Note on A20: Adam James: W/20/0433 increased development to 17 dwellings

## b3) Commitments shared accom
b3) Commitments - Shared accommodation (full permission)
Sites with full planning permission
|  |  | C2 Residential institutions | C4 Small HMOs | PBSA (purpose build student accommodation) | Sui Generis - Large HMOs
W/20/0878 | Lower Heathcote, Local Centre, Vickers Way, Harbury Lane, Warwick, CV34 6SL
Gain of: | Residential Institutions
As at: | 2023-03-31 | Under Construction
Care Home Bedrooms | 75 |  | 75
W/20/1908 | 2 Clarendon Place, Leamington Spa CV32 5QN
Gain of: | Residential Institutions
As at: | 2023-03-31 | Not Started
Care Home Bedrooms | 4 |  | 4
C4
W/20/1662 | 168 Emscote Road, Warwick, CV34 5QN
Loss of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not started
HMO Bedrooms | -5 |  |  | -5
W/20/2165 | 6 Charlotte Street, Leamington Spa, CV31 3EB
Loss of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not started
HMO Bedrooms | 1 |  |  | 1
W/20/2166 | 14 Charlotte Street, Leamington Spa, CV31 3EB
Loss of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not started
HMO Bedrooms | 1 |  |  | 1
W/21/0396 | Flat, 25 High Street, Leamington Spa, CV31 1LN
Loss of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not started
HMO Bedrooms | -6 |  |  | -6
W/21/0435 | Flat, Grist Mill, Chesterton Drive, Leamington Spa, CV31 1YJ
Loss of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not started
HMO Bedrooms | -5 |  |  | -5
W/21/0920 | 52 Bury Road, Leamington Spa, CV31 3HN
Gain of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not Started
HMO Bedrooms | 3 |  |  | 3
W/21/1495 | 1 Spencer Street, Leamington Spa, CV31 3NE
Gain of: | Small HMO 3 to 6 people
As at: | 2023-03-31 | Not Started
HMO Bedrooms | 5 |  |  | 5
W/22/0001 | 43 Buckley Road, Lillington, Leamington Spa CV32 7QG
Gain of: | Small HMO 3 to 6 people
As at: | 2024-03-31 | Not Started
HMO Bedrooms | 4 |  |  | 4
W/22/0175 | 1 Park Road, Kenilworth CV8 2GF
Loss of: | Small HMO 3 to 6 people
As at: | 2024-03-31 | Not Started
HMO Bedrooms | -5 |  |  | -5
W/22/0564 | 58A Clemens Street, Leamington Spa CV31 2DN
Gain of: | Small HMO 3 to 6 people
As at: | 2024-03-31 | Not Started
HMO Bedrooms | 4 |  |  | 4
W/23/0760 | 38 Cobden Avenue, Leamington Spa CV31 1YF
Gain of: | Small HMO 3 to 6 people
As at: | 2024-03-31 | Not Started
HMO Bedrooms | 4 |  |  | 4
W/23/0945 | 11 Hornbeam Grove, Sydenham CV31 1QX
Gain of: | Small HMO 3 to 6 people
As at: | 2024-03-31 | Not Started
HMO Bedrooms | 4 |  |  | 4
Residential Institution (Other)
W/23/1231 | 15 Beaufort Avenue, Cubbington CV32 7TA
Gain of: | Residential Institution (Children's Home)
As at: | 2024-03-31 | Not Started
Residential Institution (Other) Beds | 3 |  | 3
PBSA
W/17/1614 | 19-21 Wise Street, Leamington Spa, CV31 3AP
Gain of: | Purpose built student accommodation
As at: | 2023-03-31 | Not Started
PBSA Bedrooms | 200 |  |  |  | 200
W/20/1887 | 3 Wise Terrace, Leamington CV31 3AS
Gain of: | Purpose built student accommodation
As at: | 2023-03-31 | Not Started
HMO & PBSA Bedrooms | 1900-02-22 |  |  |  | 54
Sites with outline planning permission
|  | Total | 82 | 5 | 254 | 0
|  | Ratio to calculate equivalent dwellings | 1.9 | 2.4 | 2.4 | 2.4
|  | Equivalent dwellings | 43.1579 | 2.0833 | 105.8333 | 0
[7 empty] | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total
|  | Equivalent dwellings - residential institutions | 43.1579 |  |  |  | 14.386 | 14.386 | 14.386 |  |  | 43.1579
|  | Equivalent dwellings - students and HMO | 107.9167 |  |  |  | 35.9722 | 35.9722 | 35.9722 |  |  | 107.9167

## c) Small SHLAA Sites
c) Small SHLAA Sites
SHLAA Ref | Site | Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period
L30 | Telephone Exchange | 0 | [5 empty] | 0
L32 | Jewsons (not including Dairy site) | 0 | [5 empty] | 0
W25 | Nelson Club, Car park | 0 | [5 empty] | 0
W29 | Heathcote Hill Farmhouse | 0 | [5 empty] | 0
K15 | Talisman Theatre | 0 | [5 empty] | 0
W40 | Lock Lane | 0 | [5 empty] | 0
W43 | Idex Site, Charles Street | 0 | [5 empty] | 0
L06 | Edmondscote Manor | 0 | [5 empty] | 0
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total - less 10% | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: Michael Brown: SHLAA identified this site as suitable for 10 dwellings; now not expected to come forward for housing
Note on C4: Michael Brown: SHLAA identified this part of the site as suitable for 20 dwellings; now not expected to come forward for housing
Note on C5: Michael Brown: SHLAA identified this site as suitable for 5 dwellings; no plans to build here in the near future.
Note on C6: Michael Brown: SHLAA identified site suitable for 6 dwellings, now expected to come forward for non-residential uses
Note on C7: Michael Brown: Identified in SHLAA as suitable for 5 dwellings; now not expected to come forward for residential use.
Note on C8: Michael Brown: SHLAA identified as suitable for 20 dwellings; now not clear whether site will come forward for residential use.
Note on C9: Michael Brown: SHLAA identified as suitable for 42 dwellings; now not clear whether site will come forward for residential use.
Note on C10: Sarah Cleverley: development envisaged beyond the end of the plan period as dependent on relocation

## d) Windfalls
d) Windfalls Trajectory (based on Updated Tables for Windfalls Paper - November 2016 - Doc EXAM 136)
| Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period
TOTAL | 505 | 101 | 101 | 101 | 101 | 101 | 505

## e) Canalside & Emp Areas
e) Canalside & Employment Regeneration Areas
| Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period
Cape Road / Millers Road, Warwick | 0 | [5 empty] | 0
Common Lane, Kenilworth (industrial estate) | 0 | [5 empty] | 0
Sydenham Industrial Estate, Leamington spa | 0 | [5 empty] | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0
The sites on this sheet were identified in the Local Plan as having the potential for housing, as they are less capable of providing the right type of employment land in the right location to meet future business needs.
However as there are no current plans for regeneration, and it is not clear how much of each area might be redeveloped, it is not possible to make predictions for quantities or build-out rates

## f) Allocated Bfield Sites
f) Allocated Brownfield Sites
Local plan allocation ref | Site | Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period | Total beyond plan period
H02 (part) | Former sewage Works, Harbury Lane | 0 | [5 empty] | 0 | 300
H09 | Kenilworth school | 30 |  |  |  |  | 30 | 30 | 257
H11 (part) | Land at Montague Road (Ambulance station) | 0 | [5 empty] | 0 | 19
H12 | Kenilworth VI Form | 83 |  |  |  | 33 | 50 | 83 | 47
H14 | Riverside House | 74 |  |  |  | 10 | 64 | 74
H16 (part) | Court Street | 90 |  |  |  | 40 | 40 | 80 | 10
| Total | 277 | 0 | 0 | 0 | 83 | 184 | 267 | 633
Note on C3: Michael Brown: Local plan allocated 215 dwellings; current estimate is that 300 dwellings will be delivered here
Note on C5: Michael Brown: Local plan allocation for whole of H11 is 140 dwellings; 19 dwellings represents the residual after accounting for 121 dwellings elsewhere on H11 in the granted application W/20/0760.
Note on C7: Sarah Cleverley: Previous planning permission for this site has now lapsed. New Outline received from Homes England W/24/0609 for up to 74 dwellings. Local plan allocated 100 dwellings for this site.
Note on C8: Adam James: Local plan allocation was for 75 dwellings; W/19/0531 (up to 90 dwellings) granted subject to conditions and signing of s106.

## g) Allocated Gfield Sites
g) Allocated Greenfield Sites
Local plan allocation ref | Site | Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39
| Edge of Warwick, Leamington, Whitnash | [6 empty] | 0
H03 (part) | East of Whithash (sourthern part) | 0 | [5 empty] | 0 | 50 | 50 | 50 | 50 | 50 | 50
H45 | Land at Hazelmere/Little Acre | 0 | [5 empty] | 0 | 2029/30: 40; 2030/31: 40
| Edge of Kenilworth | [6 empty] | 0
H40 | East of Kenilworth (Woodside Conference Centre) | 55 |  |  |  | 10 | 45 | 55
H06 (part) | East of Kenilworth (Thickthorn) (northern part) | 0 | [5 empty] | 0 | 2029/30: 50; 2030/31: 50; 2031/32: 50; 2032/33: 50
| Edge of Coventry | [6 empty] | 0
H08 | Oak Lea, Finham | 0 | [5 empty] | 0 | 2029/30: 20
| Total | 55 | 0 | 0 | 0 | 10 | 45 | 55
Note on C4: Michael Brown: Remaining part of the allocation not covered by W/20/0617 expected to hold 300 dwellings, of which 50 are expected during the plan period.
Note on C5: Adam James: Allocated in Local Plan for 59, but c80 dwellings expected
Note on C8: Adam James: Rugby Club sites only

## h) Allocated Sites Villages
h) Allocated Sites Villages
Local plan allocation ref | Village | Site | Total in plan period | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | Total in plan period
H32 | Kingswood | R/O Brome Hall Lane | 1 |  |  | 1 |  |  | 1
DS22 | Leek Wootton | Former Police HQ | 70 |  | 10 | 48 | 12 |  | 70
|  | Total | 71 | 0 | 10 | 49 | 12 | 0 | 71
Note on D3: Sarah Cleverley: application in for 1 dwelling rather than 12
Note on D4: Sarah Cleverley: Plan allocation was 115. Application from Cala Homes (granted at Appeal May 2024) is for "up to 83" dwellings. RM now submitted for 70 dwellings. Figure adjusted to reflect this.

## Supply by Spatial Area (hidden)
Commitments
Row Labels | Sum of Remaining
Elsewhere | 88
Greenfield edge of Coventry | 167
Greenfield edge of Kenilworth | 96
Greenfield edge of Warwick, Leamington and Whitnash | 4845
Growth villages | 392
Urban brownfield | 1510
Grand Total | 7098
Small Shlaa Sites
Row Labels | Sum of Total | Sum of Total - 10%
Elsewhere | 15 | 13.5
Greenfield edge of Warwick, Leamington and Whitnash | 5 | 4.5
Urban brownfield | 271 | 243.9
Grand Total | 291 | 261.9
Canalside & Employment Regeneration Areas
Row Labels | Sum of Total
Urban brownfield | 200
Grand Total | 200
Allocated Brownfield Sites
Row Labels | Sum of Total
Elsewhere | 20
Urban brownfield | 910
(blank) | 0
Grand Total | 930
Allocated Greenfield Sites
Row Labels | Sum of Total
Greenfield edge of Coventry | 20
Greenfield edge of Kenilworth | 760
Greenfield edge of Warwick, Leamington and Whitnash | 900
(blank) | 0
Grand Total | 1680
Villages
Row Labels | Sum of Total
Growth Villages | 1100
Grand Total | 1100
New Allocated Sites Jan 2016
Row Labels | Sum of Total
Greenfield edge of Coventry | 2225
Greenfield edge of Kenilworth | 740
Greenfield edge of Warwick, Leamington and Whitnash | 500
(blank) | 0
Grand Total | 3465
Commitments - April and May 2016
Row Labels | Sum of Total
Growth Villages | 225
Grand Total | 225
Completions
Spatial Area | Units
Urban brownfield | 1399
Greenfield edge of Kenilworth | 8
Greenfield edge of Warwick, Leamington and Whitnash | 518
Greenfield edge of Coventry | 59
Growth villages | 126
Elsewhere | 93
Spatial Area Sub Total | 2203
Spatial Area | Units | % of Spatial Area Sub Total
Urban brownfield | 4262.9 | 24.84%
Greenfield edge of Kenilworth | 1604 | 9.345%
Greenfield edge of Warwick, Leamington and Whitnash | 6768 | 39.43%
Greenfield edge of Coventry | 2471 | 14.4%
Growth villages | 1843 | 10.74%
Elsewhere | 214.5 | 1.25%
Spatial Area Sub Total | 17163.4 | 100%
Windfalls | 505
Total | 17668.4
NB. Gross figure used for Commitments (53 losses/conversions across area)
NB. Gross figure used for Completions (101 losses/conversions across area)

## Supply by Village (hidden)
Growth Villages | Completions | Commitments | Allocations | Total
Baginton | 0 | 1 | 80 | 81
Barford | 42 | 78 | 87 | 207
Bishop’s Tachbrook | 2 | 200 | 0 | 202
Burton Green | 34 | 2 | 90 | 126
Cubbington | 7 | 12 | 195 | 214
Hampton Magna | 0 | 0 | 245 | 245
Hatton Park | 13 | 0 | 175 | 188
Kingswood | 12 | 23 | 48 | 83
Leek Wootton | 0 | 0 | 120 | 120
Radford Semele | 16 | 301 | 60 | 377
Growth Villages Sub Total | 126 | 617 | 1100 | 1843
Limited Infill Villages
Ashow | 0 | 1 | 0 | 1
Baddesley Clinton | 2 | 23 | 0 | 25
Beausale | 1 | 4 | 0 | 5
Bubbenhall | 1 | 1 | 0 | 2
Chessetts Wood | 0 | 0 | 0 | 0
Eathorpe | 0 | 0 | 0 | 0
Hampton-on-the-Hill | 0 | 0 | 0 | 0
Haseley Knob | 0 | 0 | 0 | 0 | Row Labels | Sum of Remaining | Row Labels | Sum of Total | Row Labels | Sum of Total
Hatton Green | 0 | 0 | 0 | 0 | Ashow | 1 | Growth Villages | 1100 | Bishops Tachbrook | 50
Hatton Station | 0 | 0 | 0 | 0 | Baddesley Clinton | 23 | Baginton | 80 | Radford Semele | 175
Hill wootton | 0 | 1 | 0 | 1 | Baginton | 1 | Barford | 87 | Grand Total | 225
Lapworth | 0 | 0 | 0 | 0 | Barford | 78 | Bishop’s Tachbrook | 0
Little Shrewley | 0 | 0 | 0 | 0 | Beausale | 4 | Burton Green | 90
Lowsonford | 0 | 0 | 0 | 0 | Bishop’s Tachbrook | 150 | Cubbington | 195
Norton Lindsey | 3 | 0 | 0 | 3 | Bubbenhall | 1 | Hampton Magna | 245
Offchurch | 0 | 2 | 0 | 2 | Burton Green | 2 | Hatton Park | 175
Old Milverton | 1 | 0 | 0 | 1 | Cubbington | 12 | Kingswood | 48
Rowington | 1 | 0 | 0 | 1 | Hill wootton | 1 | Leek Wootton | 120
Rowington Green | 1 | 2 | 0 | 3 | Kingswood | 23 | Radford Semele | 60
Sherbourne | 4 | 0 | 0 | 4 | Offchurch | 2 | Grand Total | 1100
Shrewley Common | 2 | 0 | 0 | 2 | Radford Semele | 126
Stoneleigh | 2 | 1 | 0 | 3 | Rowington Green | 2
Wasperton | 1 | 0 | 0 | 1 | Stoneleigh | 1
Weston-under-Wetherley | 0 | 0 | 0 | 0 | (blank) | 6555
Limited Infill Villages Sub Total | 19 | 35 | 0 | 54 | Grand Total | 6982
Villages Total | 145 | 652 | 1100 | 1897